## Sample
ATTACHMENT 31 SCHEDULE OF PAYMENTS/PAYABLE MILESTONES Task Order # 20xx-xxx-xxx Project Title
|  |  | Contract Awd:6 | 2021-02-01
Phase | Milestone2 | Deliverable Title | Due Date (DACA)5 | Due Date (Actual)7 | Program Funding | Cost Share
1 | 01 | Project Management Plan | 10 | 2021-02-11 | 5000 | 5000
1 | 02a3 | Kick-off Meeting Presentation | 20 | 2021-02-21 | 0 | 0
1 | 02b3 | Kick-off Meeting Minutes | 22 | 2021-02-23 | 1000 | 1000
1 | 03 | Quarterly Report 14 |  | 2021-03-20 | 0 | 0
1 | 04 | Initial Design | 104 | 2021-05-16 | 10000 | 10000
1 | 05 | Quarterly Technical Review Minutes 1 | 120 | 2021-06-01 | 1000 | 1000
1 | 06 | Quarterly Report 2 |  | 2021-06-20 | 0 | 0
1 | 07 | Stakeholder Survey | 190 | 2021-08-10 | 2500 | 2500
1 | 08 | Quarterly Technical Review Minutes 2 | 215 | 2021-09-04 | 1000 | 1000
1 | 09 | Quarterly Report 3 / Phase 1 Report |  | 2021-09-20 | 0 | 0
|  | Phase 1 Totals |  |  | 20500 | 20500
2 | 10 | Tech Transfer & Implementation Plan Update | 240 | 2021-09-29 | 1000 | 1000
2 | 11 | Design Update | 272 | 2021-10-31 | 10000 | 10000
2 | 12 | Initial Prototype Build | 280 | 2021-11-08 | 100000 | 100000
2 | 13 | Quarterly Technical Review Minutes 3 | 303 | 2021-12-01 | 1000 | 1000
2 | 14 | Quarterly Report 4 |  | 2021-12-20 | 0 | 0
2 | 15 | Test Results | 364 | 2022-01-31 | 100000 | 100000
2 | 16 | Quarterly Technical Review Minutes 4 | 385 | 2022-02-21 | 1000 | 1000
2 | 17 | Quarterly Report 5 |  | 2022-03-20 | 0 | 0
2 | 18 | Finalize Build | 460 | 2022-05-07 | 200000 | 200000
2 | 19 | Quarterly Technical Review Minutes 5 | 470 | 2022-05-17 | 1000 | 1000
2 | 20 | Test Results | 490 | 2022-06-06 | 10000 | 10000
2 | 21 | Quarterly Report 6 |  | 2022-06-20 | 0 | 0
2 | 22 | Final Workshop Presentation | 525 | 2022-07-11 | 20000 | 20000
2 | 23 | Final Report and Project Results Summary | 530 | 2022-07-16 | 2000 | 2000
|  | Phase 2 Totals |  |  | 446000 | 446000
|  | Project Totals |  |  | 466500 | 466500
NOTES:
1 | This Excel template must be used when developing the Task Order Attachment 3, to ensure consistent and accurate tracking of deliverables and invoices.
2 | All milestone numbers must be entered as shown above (01, 02, 03, . . . ).
3 | Multiple files for a single milestone may be submitted to DSM during a single upload event, but if multiple files for a single milestone will be uploaded separately (i.e. on separate days), the milestone must be broken out as separate sub-milestones, as shown above for the Milestone 2.
4 | Per Task Order Attachment 2, Technical and Business Reports are required to be submitted on a calendar quarterly basis. ALL Quarterly Reports must be included as milestones in the Attachment 3, as shown above, due on the 20th of Mar, Jun, Sep and Dec. If the Tech and Business Reports are to be submitted separately, they must be shown as separate sub-milestones, per note 3 above. If Quarterly Reports are designated as "no cost," enter "$0" under Program Funding and Cost Share.
5 | "DACA" means "(Calendar) Days After Contract Award." Only this column will be completed by the offeror when initially submitting the Cost Proposal.
6 | Contract Award Date, once known, to be entered by ATI while developing the Task Order .
7 | Dates will auto-calculate once Contract Award Date is filled in, except for Quarterly Report dates, which are fixed.
Formulas:
Due Date (Actual)7 = E5+[Due Date (DACA)5]
SAMPLE

## Template
ATTACHMENT 31 SCHEDULE OF PAYMENTS/PAYABLE MILESTONES Task Order # 20xx-xxx-xxx Project Title
Contract Awd:6
Phase | Milestone2 | Deliverable Title | Due Date (DACA)5 | Due Date (Actual)7 | Program Funding | Cost Share
1 | 01 | Project Management Plan |  | 0
1 | 02a3 | Kick-off Meeting Presentation |  | 0
1 | 02b3 | Kick-off Meeting Minutes |  | 0
1 |  | Quarterly Report 14 |  | 2025-03-20
1 |  |  |  | 0
1 |  |  |  | 0
1 |  | Quarterly Report 2 |  | 2025-06-20
1 |  |  |  | 0
1 |  |  |  | 0
1 |  | Quarterly Report 3 |  | 2025-09-20
|  | Phase 1 Totals |  |  | 0 | 0
2 |  | Tech Transfer & Implementation Plan Update |  | 0
2 |  |  |  | 0
2 |  |  |  | 0
2 |  |  |  | 0
2 |  | Quarterly Report 4 |  | 2025-12-20
2 |  |  |  | 0
2 |  |  |  | 0
2 |  | Quarterly Report 5 |  | 2026-03-20
2 |  |  |  | 0
2 |  |  |  | 0
2 |  | Quarterly Report 6 |  | 2026-06-20
2 |  |  |  | 0
2 |  |  |  | 0
2 |  | Final Report and Project Results Summary |  | 0
|  | Phase 2 Totals |  |  | 0 | 0
|  | Project Totals |  |  | 0 | 0
NOTES:
1 | This Excel template must be used when developing the Task Order Attachment 3, to ensure consistent and accurate tracking of deliverables and invoices.
2 | All milestone numbers must be entered as shown above (01, 02, 03, . . . ).
3 | Multiple files for a single milestone may be submitted to DSM during a single upload event, but if multiple files for a single milestone will be uploaded separately (i.e. on separate days), the milestone must be broken out as separate sub-milestones, as shown above for the Milestone 2.
4 | Per Task Order Attachment 2, Technical and Business Reports are required to be submitted on a calendar quarterly basis. ALL Quarterly Reports must be included as milestones in the Attachment 3, as shown above, due on the 20th of Mar, Jun, Sep and Dec. If the Tech and Business Reports are to be submitted separately, they must be shown as separate sub-milestones, per note 3 above. If Quarterly Reports are designated as "no cost," enter "$0" under Program Funding and Cost Share. Make sure that they match the year that the work is being completed.
5 | "DACA" means "(Calendar) Days After Contract Award." Only this column will be completed by the offeror when initially submitting the Cost Proposal.
6 | Contract Award Date, once known, to be entered by ATI while developing the Task Order .
7 | Dates will auto-calculate once Contract Award Date is filled in, except for Quarterly Report dates, which are fixed.
Formulas:
Due Date (Actual)7 = E5+[Due Date (DACA)5]